## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | USFlightMGMT:001 | Design Documentation for Backend application | Sreenath | k karteek sandeep akshay | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 22 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | USFlightMGMT:002 | Test Plan | Sreenath | k karteek sandeep akshay | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | USFlightMGMT:003 | Bootstrapping the project | sreenath | k karteek sandeep akshay | Simple | Low | RD:1 Application SetUp | RD: FlightDesinDocument_ver1 | Non-Functional |  |  |  |  | 4 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | USFlightMGMT:004 | Entity Class and TableDEsign and Populating the data | sreenath | k karteek sandeep akshay | Complex | Low | RD2: Entity Class Design and RD3: Table Design | RD: FlightDesinDocument_ver2 | Functional |  |  |  |  | 8 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | USFlightMGMT:005 | Displaying Flight Schedule for the given source, destination and date of jouney | sreenath | k karteek sandeep akshay | Average | Low | RD 4: Displaying the flight schedule | RD: FlightDesinDocument_ver3 | Functional |  |  |  |  | 16 hrs | TC_Service_01,TC_DAO_01, TC_UI_01
5 | 6 | Work session | High | USFlightMGMT:006 | Booking the Flight Ticket | sreenath | k karteek sandeep akshay | Complex | Low | RD7: Booking the Flight tkt | RD: FlightDesinDocument_ver4 | Functional |  |  |  |  | 32hrs | TC_Service_02,TC_DAO_02, TC_UI_03
6 | 7 | Work session | High | USFlightMGMT:007 | Scheduling the flight | Sreenath | k karteek sandeep akshay | Complex | Low | RD8:Scheduling the flight | RD: FlightDesinDocument_ver5 | Functional |  |  |  |  | 34hrs
7 | 8 | Work session | High | USFlightMGMT:008 | User Details | Sreenath | k karteek sandeep akshay | Complex | Low | RD9:Managing User Details | RD: FlightDesinDocument_ver6 | Functional |  |  |  |  | 32hrs
8 | 9 | Work session | High | USFlightMGMT:009 | Flight and Airport managing | Sreenath | k karteek sandeep akshay | Complex | Low | RD10:Managing Flights and Airports | RD: FlightDesinDocument_ver7 | Functional |  |  |  |  | 36hrs
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | USFlightMGMT:010 | Design Documentation fo Angular application | sreenath | k karteek sandeep akshay | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional |  |  |  |  | 14hrs
| 17 | Standard document | High | USFlightMGMT:011 | Test Plan | Sreenath | k karteek sandeep akshay | Average | Low |  |  | Non Functional |  |  |  |  | 16hrs
16 | 18 | Standard document | High | USFlightMGMT:012 | Design a home page having standard menus | Sreenath | k karteek sandeep akshay | average | Low |  |  | Functional |  |  |  |  | 12hrs
17 | 19 | Work session | High | USFlightMGMT:013 | Booking the Flight Ticket | Sreenath | k karteek sandeep akshay | Complex | Low |  |  | Functional |  |  |  |  | 36hrs
18 | 20 | Work session | High | USFlightMGMT:014 | Scheduling the flight | Sreenath | k karteek sandeep akshay | Complex | Low |  |  | Functional |  |  |  |  | 32hrs
19 | 21 | Work session | High | USFlightMGMT:015 | User Details | Sreenath | k karteek sandeep akshay | Complex | Low |  |  | Functional |  |  |  |  | 34hrs
20 | 22 | Work session | High | USFlightMGMT:016 | Flight and Airport managing | Sreenath | k karteek sandeep akshay | Complex | Low |  |  | Functional |  |  |  |  | 36hrs
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| USFlightMGMT:010 | 1 | Wireframes and story boarding for each task | k karteek sandeep akshay
|  | 2 | Routing Url List | Chinthakuntla Pedda Narasimhulu
|  | 3 | Data classes details | Nikhil Ranjan Das
|  | 4 | Angular service | Viswajeeth
|  | 5 | Components details | Deepika
| USFlightMGMT:011 | 1 | Test Plan for Booking Ticket | Deepika
|  | 2 | Test plan for scheduling | k karteek sandeep akshay
|  | 3 | Test Plan for displaying schedule | Narasimha
|  | 4 | Test plan for User details | Chinthakuntla Pedda Narasimhulu
|  | 5 | Test plan for Airport management | Nikhil ranjan Das
|  | 6 | Test plan for Flight management | Viswajeeth
| USFlightMGMT:012 | 1 | Designing menu in template | Viswajeeth
|  | 2 | Adding Routing details | Viswajeeth
|  | 3 | Displaying standard info or advertisement | Viswajeeth
| USFlightMGMT:013 | 1 | Design a form that captures no of passengers and flight schedule
|  | 2 | Component sends the details to service
|  | 3 | Angular service make the webservice call and get the Booking Id ref from the backend
|  | 4 | Design a web design to display generated booking ID or error response sent by the server
| USFlightMGMT:013 | 1 | Design a form that captures the available flights and airport to schedule and also arrival and departure time | k karteek sandeep akshay
|  | 2 | component sends the details to service | k karteek sandeep akshay
|  | 3 | Angular service make a webservice call and store/add the schedule flight to the backend | k karteek sandeep akshay
|  | 4 | Design a display page where you can see all the scheduled flights | k karteek sandeep akshay
|  | 5 | In the Display page,we add two option buttons one for delete and one for update | k karteek sandeep akshay
|  | 6 | Design a search page where you search scheduled with date ,source and destination airports entered | k karteek sandeep akshay
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | USFlightMGMT:001 | 1 | Entity Class Design | k k sandeep akshay | 2020-04-17 | 4 hrs | 2 hrs | Completed | 3
|  | 2 | Table Design | k k sandeep akshay | 2020-04-17 | 2 hrs | 2 hrs | Completed | 2
|  | 3 | Application Architecture | C pedha Narasimha | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 1
|  | 4 | Use case diagram | C pedha Narasimha | 2020-04-17 | 2 hrs | 0,5 hrs | completed | 2
|  | 5 | Sequence Diagram | Nikhil Ranjan das | 2020-04-17 | 4 hrs | 0.5 hrs | Completed | 3
|  | 6 | Each use case detail description | Nikhil Ranjan das | 2020-04-17 | 4 hrs | 0.5 hrs | Completed | 2.5
|  | 7 | Class Layer diagram | Deepika | 2020-04-17 | 1 hrs | 0.5 hrs | Completed | 1
|  | 8 | Class Diagram | Deepika | 2020-04-17 | 2 hrs | 0.5 hrs | Completed | 2
|  | 9 | Webservice URL Details | viswajeeth | 2020-04-17 | 2 hrs | 0.5 hrs | Completed | 2.5
2 | USFlightMGMT:002 | 1 | Test plan for dao, | Everyone
|  | 2 | Test plan for service | Everyone
|  | 3 | Test plan for webservice methods | Everyone
3 | USFlightMGMT:003 | 1 | Creating a Spring boot starter project | Chinthakuntla Pedda Narasimhulu | 2020-04-17 | 2 hrs | 0.5 hrs |  | 1.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | Chinthakuntla Pedda Narasimhulu | 2020-04-17 | 1 hrs | 0.5 hrs |  | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | Chinthakuntla Pedda Narasimhulu | 2020-04-17 | 1 hrs | 0.5 hrs |  | 0.5 hrs
4 | USFlightMGMT:004 | 1 | Entity Class Design | Nikhil
|  | 2 | Check tables are poulated in DB | Nikhil
|  | 3 | Populate the Data | Viswajeeth
5 | USFlightMGMT:005 | 1 | Write a JPQL query to retrieve the flight details for the given date, src and destination in DAO layer
|  | 2 | service method invoke the Dao and get the list. If list is empty throw FlightscheduleException "No Flight Found"
|  | 3 | Service method check the date of jouney is not the past date otherise throw exception
|  | 4 | REstController method get the details such as src, dest and date of journet from the url path and send to service
6 | USFlightMGMT:006 | 1 | Write the JPQL query to get the Flightschedule by flightschedule ID in DAO
|  | 2 | Write the JPQL query to get the User by User ID in DAO
|  | 3 | Write a code to insert booking instance
|  | 4 | Service checks the fligschedule , user and no of seats are avaialble
|  | 5 | If available deduts the seats from Flighschedule
|  | 6 | generate the booking ID and bind to newly created booking instance and send to DAO
|  | 7 | RestController method get the details such as flightschedule ID, no of seats, user ID and send to service method and returns Booking ID ref
7 | USFlightMGMT:007 | 1 | Write the JPQL in the DAO layer to fetch the flights and airports which are available with airport code and flightnumber reference | K karteek sandeep akshay
|  | 2 | write a code to insert schedule instance | K karteek sandeep akshay
|  | 3 | service method invoke the Dao and add the schedule flight.if we enter the schedule ID that already exists then it will throw an error "Id already exists" | K karteek sandeep akshay
|  | 4 | If entered scheduled ID is not exists then schedule instance would be added | K karteek sandeep akshay
|  | 5 | Displaying all the scheduled flights with JPQL to fetch complete schedule entity table in the DAO layer | K karteek sandeep akshay
|  | 6 | Updating the schedule instance with already existing scheduling ID | K karteek sandeep akshay
|  | 7 | write a JPQL to Fetching schedule object with the particular ID and updating it | K karteek sandeep akshay
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.